## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 92 | 0 |  |  |  | 16 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2016-10-19 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-03 | 2016-10-05 | 2016-10-07 | 2016-10-10 | 2016-10-12 | 2016-10-14 | 2016-10-17 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | ——Prepatation—— | [23 empty] | Assigned
6 | 1 | Research 2D games about rolling ball for movement | ED |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 1 | Research 2D games about rolling ball for movement | MD |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Git | ED |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 1 | Unity Merge | ED |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 1 | Unity Merge | MD |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | [25 empty] | Can't Repro
12
13
14
15 |  | ——Player——
16 | 1 | Controller input | ED |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | Moving left and right (left stick) | ED |  | 2 | 0 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1 | Jumping (RT) | ED |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2 | Wall Jump (RT) | ED |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | Color Switch - 4 (red, blue, green, yellow) (a,b,x,y) | ED |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 3 | Grappling Hook (Pull) (LT) | ED |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 4 | Grappling Hook (Swinging) | ED |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 2 | Rolling Animation | ED |  | 2 | 0 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 4 | 3 colors in center, one outside, swap + animation | MD |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3 | Player Sprites | ED |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26
27
28
29
30
31
32
33
34
35 |  | ——Mechanic——
36 | 1 | Colored Platform Functionality | ED |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 2 | Grappling Hook Power Up (Pickup) | ED |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 3 | Button changes room color | MD |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 1 | Room Definitions | MD |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 1 | Colors - 3 (Pickup) | MD |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 2 | Checkpoints | MD |  | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 3 | Checkpoint Sprites | ED |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43
44
45
46
47
48
49
50 |  | ——Environment——
51 | 4 | Hookable / Non - Hookable Surfaces | ED |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 1 | Non-Colored Surfaces | ED |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | Colored Surfaces | ED |  | 1.5 | 0 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 1 | Player follow cam & Map cam | MD |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 3 | Tron(ish) Materials | MD |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 1 | Red Area Design | MD |  | 7.5 | 0 |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 1 | Blue Area Design | MD |  | 7.5 | 0 |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 1 | Yellow Area Design | MD |  | 7.5 | 0 |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 1 | Green Area Design | MD |  | 7.5 | 0 |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 1 | Black Area Design | ED |  | 7.5 | 0 |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 3 | Background Music | ED |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 3 | Sound Effects | ED |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 1 | Pause Overlay | ED |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 1 | Game Overlay | MD |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | 5 | Final Touches | ED |  | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
108 | 5 | Final Touches | MD |  | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 16 | 16 | 14 | 12 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 92 | 92 | 80.5 | 69 | 51.75 | 40.25 | 28.75 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 59.5 | 59.5 | 59 | 56.5 | 26.5 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 5.5 | 5.5 | 5.5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 13 | 13 | 13 | 13 | 12 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 |  |  | 4 | [5 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Eric Drenckpohl | ED |  |  |  |  | ED | 43.5 | 43.5 | 43 | 38.5 | 26 | 20.5 | 18.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 |  | Michael Dobrowolski | MD |  |  |  |  | MD | 48.5 | 48.5 | 48.5 | 48.5 | 28 | 13.5 | 13.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92
236

## Daily Scrum
Producer | 2016-10-19 |  | Team Members
Approved | Dates |  | Eric Drenckpohl | Michael Dobrowolski
| 2016-10-03 | Mon | Done: Haven't started project Next: Discuss mechanic Help: | Done: Haven't started project Next: Discuss mechanic Help:
| 2016-10-04 | Tue | Done: Haven't started project Next: Discuss mechanic Help: | Done: Haven't started project Next: Discuss mechanic Help:
| 2016-10-05 | Wed | Done: Met and discussed mechanic and basic idea for the game, created burndown chart Next: Create git, and basic player movement Help: | Done: Met and discussed mechanic and basic idea for the game, created burndown chart Next: Create git, and basic player movement Help:
| 2016-10-06 | Thu | Done: Nothing today Next: Create git, and basic player movement Help: | Done: N/A Next: Rooms and camera Help:
| 2016-10-07 | Fri | Done: Created git, burndown, basic movement, and platforms of different colors that you can fall through, as well as color switching of player Next: Create hook indicator and mechanic, and research how the hook works in other games Help: Discuss the way the hook mechanic should work, and create research document | Done: N/A Next: Rooms and camera Help:
| 2016-10-08 | Sat | Done: Nothing today Next: Create hook indicator and mechanic, and research how the hook works in other games Help: Discuss the way the hook mechanic should work, and create research document | Done: N/A Next: Rooms and camera Help:
| 2016-10-09 | Sun | Done: Created hook indicator, researched a couple other games, discussed specifics of mechanic and plan for implementation Next: Create the hook, which will hit a surface and pull you towards it, as well as a power up that enables the hook ability Help: Research how to make the hooking mechanic work with any surface | Done: Rooms and some camera, designed 3 lvls, made basic rooms transistioning tool("pipe"), warning sign Next: a bit more camera work, colored power-ups, Help:
| 2016-10-10 | Mon | Done: Switched hook powerup to green color, gave each color special abilities Next: Implement hook, double jump, glide Help: Figure out best way to do animation and when to break the hook off | Done: Scrapped single level design for open world, began building level, powerups Next: more level design, lighting Help:
| 2016-10-11 | Tue | Done: implemented glide and double jump Next: implement hook Help: figure out best way to do animation and when to break the hook off | Done: Beginning of first stage, spikes, lighting Next: checkpoints, more level design Help:
| 2016-10-12 | Wed | Done: implemented hook Next: create new, more efficient graphics for hook, player, and especially spikes Help: maybe some photoshop tutorials | Done: Double jump area, camera work and background colors Next: checkpoints Help:
| 2016-10-13 | Thu | Done: Created coins, graphics for hook, coins, player, spikes Next: Add coins to all of the levels Help: ----- | Done: checkpoints, glide area Next: more level design Help:
| 2016-10-14 | Fri | Done: Finish grappling hook area, fix bugs in color changing, coin counting, and jumping Next: implement final area of level Help: research music | Done: Finished grappling hook area, fixed bugs in hook Next: touch up level design Help:
| 2016-10-15 | Sat | Done: Level design Next: final touches, justification document Help: music? | Done: -------- Next: Help:
| 2016-10-16 | Sun | Done: final touches to the levels Next: justification document Help: music liscencing? | Done: final touches to levels Next: ----- Help:
| 2016-10-17 | Mon | Done: ----- Next: justification document, music Help: liscencing? | Done: final product, justification doc Next: Help:
| 2016-10-18 | Tue | Done: Final touches, created music, the game is complete Next: Turn in the game Help: ----- | Done: Next: Help:
| 2016-10-19 | Wed | Done: Turn in the game Next: ----- Help: ----- | Done: Next: Help:
| 2016-10-20 | Thu
| 2016-10-21 | Fri
| 2016-10-22 | Sat
| 2016-10-23 | Sun
| 2016-10-24 | Mon